## Start here
Legacy → CRM Migration Kit
Read me first — how to use this workbook
If your donor records live in spreadsheets, a filing cabinet, or an ageing desktop database, this kit turns 'we should really sort our data out' into a plan you can hand to trustees.
Work through the tabs in order. By the end you will know exactly what data you hold, where it will go in your new CRM, what needs cleaning first, and who is doing what by when.
Nothing here is specific to one vendor — but if you are moving to iCHARMS, hand the completed workbook to our onboarding team and we will map straight from it.
How to use it
1 | Data Audit — list every place donor and finance data currently lives. You cannot migrate what you haven't found.
2 | Field Mapping — for each field in your old system, decide where it lands in the new CRM (and what to drop).
3 | Data Cleaning Log — record the messy records you find and how they were fixed, so nothing is silently lost.
4 | Migration Plan — the step-by-step project plan with owners, dates and a go-live checklist.
Built for UK charities by Techno Serve Solutions — makers of iCHARMS (HMRC-listed Gift Aid software). info@technoservesolutions.com · +44 7429 466754 · technoservesolutions.com

## 1. Data Audit
Data Audit Checklist
Find every source of donor, member and finance data before you move anything.
Data source | Type | Approx. records | Owner | Format | Contains personal data? | Keep / Archive / Discard | Notes
Donations spreadsheet 2019–2024 | Donations | 3,200 | Fundraising | Excel | Yes | Keep | Multiple tabs per year — needs merging
Old Access database | Donors/CRM | 1,850 | Admin | MS Access | Yes | Keep | Duplicates likely; last used 2021
Gift Aid declarations folder | Gift Aid | 900 | Finance | Paper + PDF | Yes | Keep | Scan outstanding paper declarations
Built for UK charities by Techno Serve Solutions — makers of iCHARMS (HMRC-listed Gift Aid software). info@technoservesolutions.com · +44 7429 466754 · technoservesolutions.com

## 2. Field Mapping
Field Mapping Template
Map each old field to its home in the new CRM. Decisions made here prevent data loss at go-live.
Old field / column | Source system | New CRM field | Data type | Required? | Transformation rule | Status
FullName | Access DB | First name + Last name | Text | Yes | Split on first space; review edge cases | Mapped
GiftAid (Y/N) | Donations sheet | Gift Aid declaration status | Boolean | Yes | Y→Active, blank→None | Mapped
Postcode | Access DB | Address – Postcode | Text | No | Uppercase, trim spaces | Needs review
Built for UK charities by Techno Serve Solutions — makers of iCHARMS (HMRC-listed Gift Aid software). info@technoservesolutions.com · +44 7429 466754 · technoservesolutions.com

## 3. Data Cleaning Log
Data Cleaning Log
Every fix, recorded. This is your audit trail if a trustee asks 'what happened to record X?'.
Date | Record / batch | Issue found | Action taken | Records affected | Done by | Verified?
2026-02-10 | Donations 2020 tab | Duplicate donors (name + postcode match) | Merged 42 duplicates, kept earliest ID | 42 | A. Momin | Yes
2026-02-12 | Access DB | Blank/invalid emails | Flagged 30 for follow-up, not imported | 30 | Admin | No
Built for UK charities by Techno Serve Solutions — makers of iCHARMS (HMRC-listed Gift Aid software). info@technoservesolutions.com · +44 7429 466754 · technoservesolutions.com

## 4. Migration Plan
Migration Project Plan
The plan you hand to trustees. Owners and dates make it real.
# | Phase / task | Owner | Start | Due | Status | Notes
1 | Complete data audit (Tab 1) | Ops lead | 2026-02-01 | 2026-02-14 | Done
2 | Agree field mapping with CRM supplier | Ops + supplier | 2026-02-15 | 2026-02-28 | In progress
3 | Clean & de-duplicate source data | Fundraising | 2026-03-01 | 2026-03-15 | Not started | Use Tab 3 to log
4 | Test import into sandbox | Supplier | 2026-03-16 | 2026-03-22 | Not started | Import a sample first
5 | Validate against source (spot-check 20 records) | Finance | 2026-03-23 | 2026-03-27 | Not started
6 | Full import & go-live | Supplier | 2026-03-28 | 2026-03-30 | Not started
7 | Staff training & decommission old system | Ops lead | 2026-03-31 | 2026-04-07 | Not started | Keep read-only backup 12 months
Built for UK charities by Techno Serve Solutions — makers of iCHARMS (HMRC-listed Gift Aid software). info@technoservesolutions.com · +44 7429 466754 · technoservesolutions.com