## Start here
Ramadan & Zakat Campaign Calendar
Read me first — how to use this workbook
Ramadan is when most UK Islamic charities raise the bulk of their year's income — and the season nobody can afford to plan at the last minute.
This calendar gives you a day-by-day content and appeals plan for all 30 days, a pre-Ramadan runway so you launch ready, and an Eid thank-you plan so donors hear the result.
Every theme is a starting point — swap in your own causes and stories. Pair it with the Zakat calculator (also free) so donors can work out what they owe.
How to use it
1 | Runway & Eid — the tasks to finish before Ramadan and the thank-you plan for after.
2 | 30-Day Calendar — a suggested theme, channel and ask for every day. Fill in dates and owners.
3 | Track status as you go so nothing is missed during the busiest month.
Built for UK charities by Techno Serve Solutions — makers of iCHARMS (HMRC-listed Gift Aid software). info@technoservesolutions.com · +44 7429 466754 · technoservesolutions.com

## 1. Runway & Eid
Pre-Ramadan Runway & Eid Follow-up
Win Ramadan in the weeks before it starts. Finish these, then run the 30-day calendar.
When | Task | Owner | Status | Notes
6 weeks before | Set fundraising target & flagship causes | Fundraising | Not started
4 weeks before | Build/refresh donation pages & Zakat page | Web | Not started | Test on mobile
4 weeks before | Confirm Gift Aid declarations flow works | Finance | Not started
3 weeks before | Line up beneficiary stories, photos, video | Comms | Not started | Get consent to use
2 weeks before | Schedule emails & social for week 1 | Comms | Not started
1 week before | Secure match-funding pledge & warm-up email | Fundraising | Not started
Eid | Thank every donor + share early impact | Comms | Not started | Segment by amount
Eid +2 weeks | Convert one-off donors to regular giving | Fundraising | Not started
Built for UK charities by Techno Serve Solutions — makers of iCHARMS (HMRC-listed Gift Aid software). info@technoservesolutions.com · +44 7429 466754 · technoservesolutions.com

## 2. 30-Day Calendar
30-Day Ramadan Content & Appeals Calendar
A suggested theme for every day. Add your dates, channel and owner — then work the plan.
Day | Date | Suggested theme / content | Channel | Primary ask | Owner | Status
Day 1 |  | Ramadan Mubarak — set the campaign intention & first appeal |  |  |  | Planned
Day 2 |  | The reward of giving in Ramadan (education post) |  |  |  | Planned
Day 3 |  | Beneficiary story #1 — a life your donors changed |  |  |  | Planned
Day 4 |  | Where your donation goes — transparency breakdown |  |  |  | Planned
Day 5 |  | Zakat explained — who pays and on what |  |  |  | Planned
Day 6 |  | Feed a family — food parcel appeal |  |  |  | Planned
Day 7 |  | Weekend push — announce match funding |  |  |  | Planned
Day 8 |  | Your flagship cause spotlight (water, orphans, relief) |  |  |  | Planned
Day 9 |  | Update from the field — photos/video from the ground |  |  |  | Planned
Day 10 |  | Beneficiary story #2 |  |  |  | Planned
Day 11 |  | Sponsor an orphan / recurring giving appeal |  |  |  | Planned
Day 12 |  | Midway impact update — what we've raised so far |  |  |  | Planned
Day 13 |  | Share the Zakat calculator (link the tool) |  |  |  | Planned
Day 14 |  | Sadaqah Jariyah — the gift that keeps giving |  |  |  | Planned
Day 15 |  | Video message from the founder / team |  |  |  | Planned
Day 16 |  | Beneficiary story #3 |  |  |  | Planned
Day 17 |  | Urgent need spotlight — time-limited appeal |  |  |  | Planned
Day 18 |  | Gift Aid reminder — make every £ worth 25% more |  |  |  | Planned
Day 19 |  | Weekend push #2 |  |  |  | Planned
Day 20 |  | The last 10 nights begin — countdown starts |  |  |  | Planned
Day 21 |  | Laylatul Qadr — the night better than 1,000 months (odd) |  |  |  | Planned
Day 22 |  | Multiply your reward — give tonight |  |  |  | Planned
Day 23 |  | Odd night push (23rd) |  |  |  | Planned
Day 24 |  | Automate your last-10-nights giving |  |  |  | Planned
Day 25 |  | Odd night push (25th) |  |  |  | Planned
Day 26 |  | Final week — complete your Zakat before Eid |  |  |  | Planned
Day 27 |  | Odd night push (27th) — the most sought night |  |  |  | Planned
Day 28 |  | Last chance to give this Ramadan |  |  |  | Planned
Day 29 |  | Odd night push (29th) |  |  |  | Planned
Day 30 |  | Thank you & Eid Mubarak — impact recap to all donors |  |  |  | Planned
Built for UK charities by Techno Serve Solutions — makers of iCHARMS (HMRC-listed Gift Aid software). info@technoservesolutions.com · +44 7429 466754 · technoservesolutions.com